## Annexure #22 Penalty

The Penalty applicable to the Bidder shall be independent of the Security Deposit and the Contract Performance Bond submitted by the successful Bidder.

| S. No. | Parameter | Penalty | Ceiling |
| --- | --- | --- | --- |
|  | Non-Availability of license | If the Bidder is not able to provide the license within 4 weeks of requisition by the Owner, the payment to the Bidder will be liable for deduction @0.5% of the total license price for delay of each week or part thereof. | Total price of Licenses as per the Owner’s requisition. |
|  | Non-Availability of required & agreed man-power from Implementation partner / ERP product OEM | If the Bidder is not able to provide the required & agreed man-power from ERP product OEM (Section 7.7 Resources for Solution Expert Consulting Services)/ Implementation Partner (Section 5.8 Resources for Amendments & Variations) within 15 days from the scheduled date of deployment, the payment to the Bidder shall be liable for deduction at the rate of INR 20,000 (Rupees Twenty Thousand) per manpower resource per day. | Total price as per Annexure # 18.1 OR 18.2, as applicable. |
|  | Non-Adherence to overall Project timelines | If the Bidder fails to achieve the completion of project within defined duration, the payment to him will be liable for deduction @0.5% of the total contract price for delay of each week or part thereof. | 10% of the total contract price. |
|  | Non-Adherence to Milestone timelines | If the Bidder fails to achieve the completion of any milestone within defined duration, the payment to him will be liable for deduction @0.5% of the milestone payment for delay of each week or part thereof. ** For the purpose of penalty, the period of completing the Business Blueprint milestone is reckoned as 12 months without affecting the total time schedule of the project. | Total payment linked to the respective milestone. |
|  | Non-Adherence to minimum resource requirement | If the Bidder fails to deploy the minimum resources as mentioned in Section 7.6 Minimum Resource Deployment and/ or 8.2 Minimum Resource Deployment from the date the Contract becomes effective, the payment to the Bidder shall be liable for deduction at the rate of INR 20,000 (Rupees Twenty Thousand) per manpower resource shortfall for each day. | Total Implementation Price as per Annexure # 20. |
|  | Non-compliance or non-implementation of corrections arising out of periodic Quality Audits. | If the Bidder fails to deliver the recovery compliances or implementation of corrections arising out of periodic Quality Audits, the payment to the Bidder will be liable for deduction @0.5% of the total Implementation Price for each non-compliance. | Total Implementation Price as per Annexure # 20. |
|  | Penalties for non-adherence to Helpdesk SLA parameters.. Severity of Violation; Measurement. Critical; The Critical defects should be resolved within 90 Minutes from the time of reporting full details. For the calculation of penalty, the Owner will calculate the number of violations by the Bidder every month. The calculation will be done as per the following table: % defects resolved within 90 Minutes; No. of Violations considered. <100% & >=95%; 0. < 95% & >= 90%; 1. < 90% & >= 85%; 2. < 85%; 3.. Urgent; The Urgent defects shall be resolved within 4 Hours from the time of reporting full details. This service level will be monitored on a monthly basis. For the calculation of penalty, the Owner will calculate the number of violations by the Bidder over the Quarter. The calculation will be done as per the following table: % defects resolved within 4 Hours; No. of Violations considered. <100% & >=95%; 0. < 95% & >= 90%; 1. < 90% & >= 85%; 2. < 85%; 3.. High; The High defects shall be resolved within 2 days from the time of reporting full details. This service level will be monitored on a monthly basis. For the calculation of penalty, the Owner will calculate the number of violations by the Bidder over the Quarter. The calculation will be done as per the following table: % defects resolved within 2 Days; No. of Violations considered. < 100% & >= 90%; 1. < 90% & >= 80%; 2. < 80%; 3.. - Monthly performance evaluation will be conducted by the Owner. - Penalty Calculations - The framework for Penalties, as a result of not meeting the Service Level Targets is as follows: - The performance will be measured monthly for each of the defined service level metric against the minimum / target service level requirements and the violations will be calculated accordingly. - The number of violations in the reporting period for each level of severity will be totalled and used for the calculation of Penalties. - Penalty applicable for each of the Critical, Urgent, & High severity violations is INR 10,000 (INR Ten thousand) per violation. - For violation calculation every month, the defects closing date in that particular month will be considered.. |

Note: The total cumulative penalty for the above shall not exceed 10% of the total Contract Price.