## Sheet1
Project Phase | Deliverables | Payment(%) | Implemented Locations | Schedule | Criteria for Payment
Project Preparation | Section 9.12.1 | 5% (Against equivalent amount of Bank Guarantee as per Annexure #8) | - | Actual Completion | Acceptance of all deliverables by Owner.
Business Blueprint | Section 9.12.2 | 10% | - | Actual Completion | Acceptance of all deliverables by Owner.
Realization | Section 9.12.3 | 5% | - | Actual Completion | Acceptance of all deliverables by Owner.
Phase-I Final Preparation & Go-Live | Section 9.12.4, 9.12.5 | 8% | HEP Bhopal, RMSG (Previously PDX, Bhopal) | Actual Completion | Acceptance of all deliverables by Owner.
Phase-I Final Preparation & Go-Live | Section 9.12.4, 9.12.5 | 8% | HEEP, Haridwar CFFP, Haridwar | Actual Completion | Acceptance of all deliverables by Owner.
Phase-I Final Preparation & Go-Live | Section 9.12.4, 9.12.5 | 8% | HPBP Trichy SSTP Trichy Thirumayam Plant IVP Goindwal HPVP, Visakhapatnam | Actual Completion | Acceptance of all deliverables by Owner.
Phase-I Final Preparation & Go-Live | Section 9.12.4, 9.12.5 | 5% | Power Sector Marketing, New Delhi PEM – Project Engineering Management, Noida One of the 4 PS regions including all its sites Project Management Group, New Delhi Others Industry sector New Delhi International operations New Delhi Spares & Services Business group, New Delhi | Actual Completion | Acceptance of all deliverables by Owner.
Phase-I Final Preparation & Go-Live | Section 9.12.4, 9.12.5 | 4% | Corporate Functions CEPD – Corporate Engineering and Product Development Corporate Finance Corporate Monitoring Corporate MM CMT&IP – Corporate Manufacturing Technology & Investment Planning Corporate Planning & Development Corporate Quality Advanced Research Projects | Actual Completion | Acceptance of all deliverables by Owner.
Phase-II Final Preparation & Go-Live | Section 9.12.4, 9.12.5 | 5% | BAP Ranipet | Actual Completion | Acceptance of all deliverables by Owner.
Phase-II Final Preparation & Go-Live | Section 9.12.4, 9.12.5 | 5% | Jhansi | Actual Completion | Acceptance of all deliverables by Owner.
Phase-II Final Preparation & Go-Live | Section 9.12.4, 9.12.5 | 5% | EMRP Mumbai HERP Varanasi IP, CSU Jagdishpur CFP Rudrapur | Actual Completion | Acceptance of all deliverables by Owner.
Phase-II Final Preparation & Go-Live | Section 9.12.4, 9.12.5 | 4% | Corporate Functions Corporate R&D, Hyderabad CMG, New Delhi Power Sector PSHQ – Power sector head quarter, New Delhi Balance PS regions including all their sites System Integrators ISG – Industrial systems group – Bangalore TBG – Transmission Business group – Delhi Others ROD – Regional operations division (HQ - New Delhi and Offices) Industrial operations HRDI, Noida | Actual Completion | Acceptance of all deliverables by Owner.
Phase-III Final Preparation & Go-Live | Section 9.12.4, 9.12.5 | 8% | HPEP Hyderabad unit PESD Hyderabad | Actual Completion | Acceptance of all deliverables by Owner.
Phase-III Final Preparation & Go-Live | Section 9.12.4, 9.12.5 | 5% | EDN Bangalore EPD Bangalore | Actual Completion | Acceptance of all deliverables by Owner.
Business Intelligence & Dashboards – Corporate MIRs | Section 9.13 | 10% | Owner’s all locations & Corporate | Actual Completion | Acceptance of all deliverables by Owner.
Center of Excellence | Section 9.14 | 5% | Owner’s central location | Actual Completion | Acceptance of all deliverables by Owner.
Security Deposit will be retained by the Owner till the Completion of Post Go-Live Support (section 8.8.2) period or 48 months from start of Project, whicever is later, as certified by Owner. Payment on completion of Project preparation shall be against equivalent amount of Bank Guarantee as per Annexure #8 will be retained by the Owner till the Commencement of Post Go-Live Support (section 8.8.2) period or 36 months from start of Project, whicever is later, as certified by Owner.
** Security Deposit shall be invoked by the Owner in case of: (a) Non-performance of any scope of Contract entered into with the Owner till commencement of Post Go-Live Support (section 8.8.2) period, duly certified by the Owner (b) Non-provision of support services during Post Go-Live Support (section 8.8.2) period (ref. section 8.8) (b) Non-rectification of problems arising during Post Go-Live Support (section 8.8.2) period (ref. section 8.8)
** Owner reserves the right to change the roll-out locations during final discussion with Successful Bidder depending on the ease of roll-out and geographical constraints without any implications on overall timeframe & payments.